## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
# | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | Query product (main page) | Home page | Medium | Iteration 1 | SE151492 | Đinh Văn Thành An |  | Nhóm 6
2 | Main banner (main page) + Link icon (facebook, gmail, phone) | Main page | Simple | Iteration 1 | SE151492 | Đinh Văn Thành An |  | SE150972 | Nguyễn Huỳnh Phi
3 | Search (ajax) | Search | Medium | Iteration 1 | SE150972 | Nguyễn Huỳnh Phi |  | SE150997 | Nguyễn Hoài Phương
4 | Sort product (category, price, a-z,..) | Sort | Complex | Iteration 1 | SE150997 | Nguyễn Hoài Phương |  | SE151068 | Đào Đức Thành
5 | Header (category, icon...) | Header | Simple | Iteration 1 | SE150972 | Nguyễn Huỳnh Phi |  | SE151077 | Phạm Quốc Thịnh
6 | Product information (review list, product detail) | Product detail | Complex | Iteration 1 | SE151077 | Phạm Quốc Thịnh |  | SE151492 | Đinh Văn Thành An
7 | Buy product (add product to cart) | Buy product | Medium | Iteration 1 | SE151068 | Đào Đức Thành
8 | Login (Google) + Insert user information to database + Divine role user | Login | Medium | Iteration 1 | SE151068 | Đào Đức Thành
9 | Logout | Logout | Simple | Iteration 1 | SE150972 | Nguyễn Huỳnh Phi
10 | Select new product for admin (data table) | product admin | Simple | Iteration 2 | SE151492 | Đinh Văn Thành An
11 | Preview new product information (modal) | Product admin | Simple | Iteration 2 | SE151492 | Đinh Văn Thành An
12 | Select product available on website (data table) | Delete product admin | Simple | Iteration 2 | SE151492 | Đinh Văn Thành An
13 | Delete product (sweet alert) | Delete product admin | Simple | Iteration 2 | SE151492 | Đinh Văn Thành An
14 | Dashboard | Admin dashbroad | Complex | Iteration 2 | SE151068 | Đào Đức Thành
15 | Select new reivew ticket + Approve function (data table + modal) | review admin | Medium | Iteration 2 | SE151068 | Đào Đức Thành
16 | Select user on website + promote + demote role user (data table + modal) | role admin | Medium | Iteration 2 | SE150997 | Nguyễn Hoài Phương
17 | Upload new product (multiple image, product detail) + preview on website | Create product | Complex | Iteration 2 | SE150972 | Nguyễn Huỳnh Phi
18 | Cart (CRUD on real time) | Cart | Complex | Iteration 2 | SE151077 | Phạm Quốc Thịnh
19 | Update + Select user information (image, user information) (data table + modal) | User information | Simple | Iteration 2 | SE150997 | Nguyễn Hoài Phương
20 | Query review ticket available on website Delete + Search review tickets (data table + modal) | Delete review admin | Simple | Iteration 2 | SE150997 | Nguyễn Hoài Phương