## Week 1
PROJECT REPORT
Group | <Group 6>
Week | <05/09/2022-10/09/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | In Progress | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | In Progress | Overall contents as listed in the part I of the SRS document.
3 | Screen layouts of the system functions | In Progress | Listed in the part II located in SRS documents.
4 | Web Skeleton | In Progress | HTML, CSS, JS files.
5 | Design Document | In Progress | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | PhiNH | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | PhiNH, PhuongNH | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | PhiNH, PhuongNH | List all the functions of the website.
4 | Web Skeleton | AnDVT, PhuongNH, ThanhDD, ThinhPQ | Coding HTML, CSS, JS for website.
5 | Design Document | ThanhDD, ThinhPQ | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | PhuongNH | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Create Diagram in SRS document | In Progress | Lack of experience in drawing Diagrams located in SRS documents.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Design template of web | 2022-09-17 | Requirements, layout, function.
2 | Weekly Report | 2022-09-17 | Fill in all the sections in the Excel Weekly Report file.
3 | SRS Template | 2022-09-17 | Overall contents as listed in the part I of the SRS document.
4 | Web Skeleton | 2022-09-17 | HTML, CSS, JS files.
5 | Design Document | 2022-09-17 | Overall contents as listed in the part I of the Design Document.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFE0 Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE8 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 2
PROJECT REPORT
Group | <Group 6>
Week | <12/09/2022-17/09/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | Completed | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | Completed | Overall contents as listed in the part I of the SRS document.
3 | Screen layouts of the system functions | Completed | Listed in the part II located in SRS documents.
4 | Web Skeleton | Completed | HTML, CSS, JS files.
5 | Design Document | Completed | Overall contents as listed in the part I of the Design Document.
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | PhiNH | List functions, features, complexity, planned code iteration, divide task for members.
2 | SRS Template | PhiNH, PhuongNH | Complete the sections in the SRS document like Introduction, Diagram, Screen Flow, …
3 | Screen layouts of the system functions | PhiNH, PhuongNH | List all the functions of the website.
4 | Web Skeleton | AnDVT, PhuongNH, ThanhDD, ThinhPQ | Coding HTML, CSS, JS for website.
5 | Design Document | ThanhDD, ThinhPQ | Design the package diagram, write package descriptions, design database schema and write table descriptions.
6 | Weekly Report | PhuongNH | Write a detailed report on the team's work for the week.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Create Diagram in SRS document | Completed | Lack of experience in drawing Diagrams located in SRS documents.
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Design Database | 2022-09-24 | Design ERD, collect data.
2 | Coding Funtions | 2022-09-24 | Coding functions of web.
3 | Weekly Report | 2022-09-24 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAfoGOFFA Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C23: ====== ID#AAAAfoGOFE4 Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 3
PROJECT REPORT
Group | <Group 6>
Week | <12/09/2022-17/09/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | In Progress | List functions, features, complexity, planned code iteration, divide task for members. (Iteration 1)
2 | SRS Template | In Progress | Detailed contents for the relevant assigned functions of the iteration. (Part II) (Iteration 1)
3 | Design Document | In Progress | Detailed contents for the relevant assigned functions of the iteration . (Part II & III) (Iteration 1)
4 | Build database | Completed | Create tables and insert data into DB.
5 | Coding Funtions | In Progress | Code funtion for web page.
6 | Upgrade UI/UX | In Progress | Style layout (responsive,...).
7 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | PhiNH | List functions, features, complexity, planned code iteration, divide task for members. (Iteration 1)
2 | SRS Template | PhiNH, PhuongNH | Detailed contents for the relevant assigned functions of the iteration. (Part II) (Iteration 1)
3 | Design Document | ThanhDD, ThinhPQ | Detailed contents for the relevant assigned functions of the iteration . (Part II & III) (Iteration 1)
4 | Build database | ThanhDD, ThinhPQ, PhuongNH | Create tables and insert data into DB.
5 | Coding Funtions | ThanhDD, ThinhPQ, PhuongNH,AnDVT,PhiNH | Code function follow backlog.
6 | Upgrade UI/UX | AnDVT, PhuongNH,PhiNH | Style layout (responsive,...).
7 | Weekly Report | PhuongNH | Fill in all the sections in the Excel Weekly Report file.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Upgrade UI/UX | In Progress | Set responsive for website (PC, Tablet, Phone)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Backlog Template | 2022-10-01
2 | SRS Template | 2022-10-01
3 | Design Document | 2022-10-01
4 | Coding Funtions | 2022-10-01
5 | Upgrade UI/UX | 2022-10-01
6 | Weekly Report | 2022-10-01
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAgomr01g Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C25: ====== ID#AAAAgomr01Y Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue

## Week 4
PROJECT REPORT
Group | <Group 6>
Week | <26/09/2022-01/10/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Backlog Template | Completed | List functions, features, complexity, planned code iteration, divide task for members. (Iteration 1)
2 | SRS Template | Completed | Detailed contents for the relevant assigned functions of the iteration. (Part II) (Iteration 1)
3 | Design Document | Completed | Detailed contents for the relevant assigned functions of the iteration . (Part II & III) (Iteration 1)
4 | Coding Funtions | Completed | Code funtion for web page (Iteration 1)
5 | Upgrade UI/UX | In Progress | Style layout (responsive,...).
6 | Weekly Report | Completed | Fill in all the sections in the Excel Weekly Report file.
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Backlog Template | PhiNH | List functions, features, complexity, planned code iteration, divide task for members. (Iteration 1)
2 | SRS Template | PhiNH, PhuongNH | Detailed contents for the relevant assigned functions of the iteration. (Part II) (Iteration 1)
3 | Design Document | ThanhDD, ThinhPQ | Detailed contents for the relevant assigned functions of the iteration . (Part II & III) (Iteration 1)
4 | Coding Funtions | ThanhDD, ThinhPQ, PhuongNH,AnDVT,PhiNH | Code function follow backlog.
5 | Upgrade UI/UX | AnDVT, PhuongNH,PhiNH | Style layout (responsive,...).
6 | Weekly Report | PhuongNH | Fill in all the sections in the Excel Weekly Report file.
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
| Upgrade UI/UX | In Progress | Set responsive for website (PC, Tablet, Phone)
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Backlog Template | 2022-10-08 | List functions, features, complexity, planned code iteration, divide task for members. (Iteration 2)
2 | SRS Template | 2022-10-08 | Detailed contents for the relevant assigned functions of the iteration. (Part II) (Iteration 2)
3 | Design Document | 2022-10-08 | Detailed contents for the relevant assigned functions of the iteration . (Part II & III) (Iteration 2)
4 | Coding Funtions | 2022-10-08 | Code funtion for web page (Iteration 2)
5 | Upgrade UI/UX | 2022-10-08 | Style layout (responsive,...).
6 | Weekly Report | 2022-10-08 | Fill in all the sections in the Excel Weekly Report file.
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
Note on C5: ====== ID#AAAAgomr01c Author (2022-09-16 14:08:39) Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C21: ====== ID#AAAAgomr01U Author (2022-09-16 14:08:39) Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue